Working Group proposal :-

Summer Schools in Data Science and Cloud Computing in the Developing World

Working Group Charter

The goal of the WG is to set up the framework to run a series of Summer Schools in Data Science and Cloud Computing in the Developing World. It will run at a variety of locations but will have a base in the developing world and the UK. This series would be endorsed by both the RDA and CODATA and would make use of the wide variety of expertise within these organisations. In the 18 month period of the WG it will

- Arrange funding for an initial period for the school to run (five years).

- Organise partnerships with Developing World institutions.

- Determine the best curriculum for the school in collaboration with others.

- Arrange how the materials can also be delivered online.

Value Proposition

Research in the Developing World is hampered by a variety of infrastructural issues. Access to research data in the public domain and the computational resources to analyse them, would give researchers in the Developing World the chance to do world-class research that is relevant to their society. Distributed computing techniques, for example cloud computing, present the possibility to sidestep the infrastructural difficulties. In order for this to happen, researchers need to understand the techniques of Data Science and the use of cloud computing. By training individuals who will ultimately pass on their training over a comparatively short period of time the level of understanding of this field can be built up and impact research. The creation of a cadre of individuals who can analyse, maintain and curate data sets will be an important skill which will also positively impact the local society as enterprises based on data analysis will expand.

Engagement with existing work in the area:

There exist a number of initiatives that provide training in these fields; for example there are a number of Summer Schools in Europe on cloud computing (see attached document of links). Microsoft Research provide training sessions on their cloud Azure.  There are now two MOOC’s in Data Science and the number of masters programmes in this area in expanding rapidly. Analysis platforms such as R have an ever-expanding set of teaching resources. The Software Carpentry movement, which has many of the correct pedagogical approaches for this school has events across the developed world (and has had sessions in South Africa). AidData have provided training in the analysis of social data in the developing world. The Wellcome Trust has provided funding for a successful series of schools in Bioinformatics in the Developing World. The  Accelerated Data Programme of the International Household Panel Survey, and the IHPS in general provide tools and training to many developing country institutions, to increase the availability and quality of survey data.

Within the RDA there is a proposal for an IG in training in Data Science.  CODATA has longstanding activities to build capacity in countries with developing and emerging economies.  These include:

- The PASTD Task Group (Preservation of and Access to Scientific and Technical Data in/for/with Developing Countries) has run a series of workshops in developing countries.  The next will be in Nairobi, Kenya in August 2014.

- CODATA China, with support from the Chinese Academy of Science, is running a training workshop in Big Data for Science for Researchers from Countries with Developing and Emerging Economies.

We have already made contacts with a variety of the above different organisations. CODATA is very happy to participate and to be a co-sponsor of the group.  AidData has expressed an interest in the proposal. A new IG is being formed on the teaching and training of Data Science and they can provide guidance on what the curriculum should be. The Wellcome Trust has expressed a willingness to provide guidance based on their experience.

Adoption Plan:

Final Deliverables :-

- Identify set of potential funders.

- Agreements from relevant partners to provide technical support for online materials. This will involve a breakdown of what the online materials will provide, the level of support that needs to be provided to develop and maintain these resources.

- Agreements from institutions willing to run the school. Each agreement will be an MoU that the institution will host and provide the logistical resources to make the school happen. As outlined in the timeline below, this will be completed for the 5th RDA plenary. On the basis of the first two agreements the RDA council and CODATA will be called upon to endorse the proposal.

- Funding organized for the first five years. This is to provide funding to run the schools and associated costs as well as pay for relevant staff to develop the teaching materials. News on funding will be made at the 6th RDA plenary.

- The outline for a typical Summer School. This will include a breakdown of the curriculum, methods of assessment, requirements in terms of technical resources and the organization of lectures and labs. At this point the proposed IG on education on Data Science, with whom this WG will liaise with, will be able to provide a detailed breakdown of what that curriculum should be.

The timeline for this is as follows :-

| Deliverable | Sep-Oct 14 | Nov-Dec-14 | Jan-Feb-15 | Mar-Apr-15 | May-Jun-15 | Jul-Aug-15 | Sep-Oct-15 | Nov-Dec-15 | Jan-Feb-16 | Mar-16 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Identify set of potential funders for school. |  |  |  |  |  |  |  |  |  |  |
| Agreements from partners on delivery of online resources. |  |  |  |  |  |  |  |  |  |  |
| Agreements from institutions to act as host. |  |  |  |  |  |  |  |  |  |  |
| Funding |  |  |  |  |  |  |  |  |  |  |
| Outline for School |  |  |  |  |  |  |  |  |  |  |
| RDA 4 |  |  |  |  |  |  |  |  |  |  |
| RDA 5 |  |  |  |  |  |  |  |  |  |  |
| RDA 6 |  |  |  |  |  |  |  |  |  |  |
| RDA 7 |  |  |  |  |  |  |  |  |  |  |

Intermediate documents.

The documents for this WG are as follows:

1.1 List of potential funders, relevant calls, reasoning behind approaching them and likelihood of success.

2.1 Template agreement with online delivery partners.

3.1 Template MoU with hosting institution.

3.2 Draft endorsements from RDA and CODATA.

4.1 Detailed budget for proposal.

4.2 Draft proposal.

5.1 Curriculum for schools, including learning outcomes and forms of assessment.

5.2 Detailed summary of requirements from hosting institution.

Operation

WG meetings will be based on bi-monthly on-line meetings which will review progress on the above Gantt diagram. The co-chairs will meet and discuss on a more regular (weekly) basis. In order to achieve consensus or resolve conflicts, the WG will consult with the IG on Data Science Education and defer to decisions that they make.  The WG will reach out to the parties mentioned above and liaise with a number of discipline specific IG’s and WG’s within the RDA including the Wheat Data Interoperability WG, Agricultural Data Interoperability IG, Big Data Analytics IG, Biodiversity Data Integration IG, Digital Practices in History and Ethnography IG, Geospatial IG, Marine Data Harmonisation IG, RDA/CODATA Materials, Infrastructure and Interoperability IG, Research data needs of the Photon and Neutron community, Structural Biology IG and Toxicogenomics Interoperability IG by contacting directly their chairs and asking for the opinion and feedback on the WG’s goals.

Initial Membership: A specific list of initial members of the WG and a description of initial leadership of the WG.

Hugh Shanahan, Royal Holloway, University of London (co-Chair)

Andrew Harrison, University of Essex (co-Chair)

Simon Hodson, Executive Director, CODATA

Miguel-Angel Sicilia, University of Alcalá

George Alter, University of Michigan

Ming Chen, Zhejiang University

Prof. Liu Chuang, Chinese Academy of Sciences

Yuri Demechenko, University of Amsterdam

Caroline Dynes, Royal Society

Fabrizio Gagliardi, Barcelona Supercomputer Centre

Sara Graves, University of Alabama in Hunstville

Albert Heyrovsky, University of Edinburgh

Meredith Jacob, American University

Nicky Mulder, Cape Town University

Tommi Nyronen, CSC Finland (Elixir)

Kay Raseroka, University of Botswana

Kenji Takeda, Microsoft Research

Jonathan Tedds, University of Leicester

Esther Dzale Yeumo, INRA

Amye Kenall, Biomed Central

Avgoustinos Constantinides, IBSAC Intelligent Business Solutions

Cheng Liu, University of Notre Dame

Godwin Yeboah, Aberdeen University

Rainer Stotzka, Karlsruhe Institute of Technology

Siddeswara Guru, University of Queensland

Suchith Anand, University of Nottingham

Yuri Malitsky, University College Cork

Zhijie Zhang, Fudan University